## Slide 1
Understanding a Work Order
CREW LEADER
WEATHERIZATION ASSISTANCE PROGRAM STANDARDIZED CURRICULUM – August 2012
GJA 2024 Version III
1
Notes: 1.7.2013
<number>
August 2012
‹#›

## Slide 2
By attending this session, participants will be able to:
    List basic work order components.
    Discuss simple materials procurement methods.
    Give examples of how to correct work order errors and oversights.
    Demonstrate planning job flow to execute a work order.
Learning Objectives
GJA 2024 Version III
2
Notes: 1.7.2013
By attending this session, participants will be able to:
List basic work order components.
Discuss simple materials procurement methods.
Give examples of how to correct work order errors and oversights.
Demonstrate planning job flow to execute a work order.
<number>
August 2012
‹#›

## Slide 3
Pre-Job Planning
Photo courtesy of Maine State Housing Authority
GJA 2024 Version III
3
Notes: 1.7.2013
When performing pre-job planning, be sure to:
Review the work order.
Set work date and time with the homeowner.
Plan the job flow.
Arrange for materials to be on site.
Possible sources:
Truck inventory
Community Action Agency (CAA) warehouse
Local supplier
<number>
August 2012
‹#›

## Slide 4
Pre-Job Planning
(1 hour)
Pre-Job Planning – Exercise #1
GJA 2024 Version III
4
Notes: 1.7.2013
(Refer to the Lesson Plan for instructions.)
<number>
August 2012
‹#›

## Slide 5
Anytown CAA
Anytown, USA
Purchase Order
To: AnytownWeatherizers
Anytown, USA
Anytown CAA
Contact: Andy Auditor
(XXX)XXX-XXXX
Client: John Homeowner
92 Norton Hill Road
Anytown, USA
(XXX) XXX-XXXX (Call after 8:00 AM)
Turn onto Norton Hill Rd from Main Street
@ AnytownPO. Yellow House 0.6 mile on right.
Typical Work Order
GJA 2024 Version III
5
Notes: 1.7.2013
The face sheet of a typical work order should contain:
CAA name and address.
Crew or contractor identification.
Client contact information.
Directions.
Positive identification of client home.
Use slides 5 through 11 during the guided discussion of the Pre-Job Planning Exercise, as described in the Lesson Plan.
<number>
August 2012
‹#›

## Slide 6
Floor Plan
Unheated
Kitchen
Den
Living
Bath
BR
Garage
Shed
Stair
OpenPorch
16’
26’
15’
12’
8’
16’
Green = Conditioned space
7’ cellar under main house
Den & Kitchen Floor
≈ 1 foot clearance to ground
Second floor
12’
N
BR
BR
H
13’
First Floor
GJA 2024 Version III
6
Notes: 1.7.2013
The floor plan of the client home should show:
Orientation – which way is north?
Conditioned space.
Necessary dimensions.
Clarifying notes/information.
<number>
August 2012
‹#›

## Slide 7
    Carefully air seal the wall between the kitchen and shed by stuffing large holes with scrap fiberglass and sealing over with spray foam. Seal wire penetrations with spray foam. Install weather strip and door sweep on the door. Materials: Scrap batt fiberglass, two cans expanding one-part foam, one Porta Seal weather-strip, one flex steel door sweep, and two tubes of silicone caulk.
    Install continuous 6 mil poly ground cover under kitchen and rear addition. Material: 300 sq’ 6 mil poly.
    Install 1.5 sone bath fan vented to gable end as per State Technical Manual (STM), using 4 in. metal duct sloped slightly to the exterior. Seal all joints. Insulate duct. Materials: 1 bath fan, 8 ft. of 4 in. metal duct, one 4 in. elbow, 1 qt RDC#6, 1 exterior vent hood, 10 feet of 4 in. duct insulation.
    Seal around main house chimney flashing as per STM. Material: 1-quart plastic roof cement.
    Seal all furnace ductwork. Material: 1 gallon RDC#6 mastic, two rolls of web-type drywall tape.
    Air seal all penetrations from living space to attics as per STM. Material: 1 can of one-part foam for plumbing vent stack & around new bath fan, 2 tubes caulk for all wire penetrations, 4 sq ft. galvanized steel & 1 tube high-temperature caulk for chimney chase.
Task List #1
GJA 2024 Version III
7
Notes: 1.7.2013
The list of measures to be installed should include:
A list of necessary materials with approximate amounts.
Clear installation instructions (when needed).
Specific task locations.
<number>
August 2012
‹#›

## Slide 8
    Replace existing hatch (include photos) with new airtight, insulated attic hatch as per STM. Materials: 4 sq. ft. ¾ in. AC plywood, 20 ft. #2 pine 1 in. x 4 in., 8 ft. weatherstrip, two 3 in. hooks & eyes, 8 sq. ft. 2 in. rigid foam insulation (2 layers), misc. fasteners.
    Tag location of any knob and tube (K&T) wiring to be buried by attic insulation.
    Dense pack main house slopes with cellulose as per STM. Material: 416 sq. ft. x 6 in.
    Install 12 in. cellulose on attic flats as per STM. Material: Main house = 204 sq. ft., kitchen ell = 180 sq. ft., rear addition = 128 sq. ft.
    Dense pack all walls with cellulose as per STM. Material: 945 sq. ft. x 4 in.
    Weatherstrip and door sweep front & rear doors as per STM, Materials: Two Q-lon™ weather-strips, two Flex-steel™ door sweeps.
    Close off uphill basement window. Materials: 3 sq. ft. ¾ in CDX, 1 qt. wood primer, necessary caulk & fasteners.
    Insulate box sills in basement & crawl spaces per STM using two-part foam. Be sure that two-part foam seals to 6 mil poly ground cover and first floor sub-flooring. Materials: One 200 board feet two-part foam kit.
Task List #2
GJA 2024 Version III
8
Notes: 1.7.2013
(Continuation of actual task list from first slide.)
<number>
August 2012
‹#›

## Slide 9
Items From Truck Inventory
    Four tubes silicone caulk
    Ten ft. of 4 in. duct
    insulation
    Three cans one-part foam
    One tube high
    temperature caulk
    Four sq. ft. ¾ in. AC
    plywood
    Two hooks & eyes
    Eight ft. neoprene bulb
    (bulk roll) weatherstrip
    Wiring tags
    Three sq. ft. of
    ¾ in. CDX plywood
    Fasteners (screws – nails)
    Scrap fiberglass batt
GJA 2024 Version III
9
Notes: 1.7.2013
After reviewing the work order, determine which materials will come from where.
These materials are already on the truck:
Four tubes silicone caulk
Ten ft. of 4 in. duct insulation
Three cans one-part foam
One tube high temperature caulk.
Four sq. ft. ¾ in. AC plywood
Two hooks and eyes
Eight ft. neoprene bulb (bulk roll) weatherstrip
Wiring tags
Three sq. ft. of ¾ in. CDX plywood
Fasteners (screws – nails)
Scrap fiberglass batt
<number>
August 2012
‹#›

## Slide 10
These items are in the warehouse and should be loaded into the truck before heading out to the job.
    One 200 board foot two-part foam kit
    One gallon RDC#6 mastic
Items from CAA Warehouse
GJA 2024 Version III
10
Notes: 1.7.2013
These items are in the warehouse and should be loaded into the truck before heading out to the job.
One 200 board foot two-part foam kit
One gallon RDC#6 mastic
<number>
August 2012
‹#›

## Slide 11
    One PortaSeal™ weatherstrip
    One Flexsteel™ door sweep
    Three hundred sq. ft. 6 mil poly
    One 100 CFM bath fan
    Eight ft. of 4 in. metal duct
    One 4 in. elbow
    One exterior vent hood
    One quart plastic roof cement
    Two rolls web-type drywall tape
    Four sq. ft. galvanized steel sheet metal
    Twenty ft. #2 pine 1 in. x 4 in.
    Eight sq. ft. 2 in. rigid foam insulation
    Two Q-lon™ weatherstrips
    Two Flex-steel™ door sweeps
    One quart wood primer
GJA 2024 Version III
11
Notes: 1.7.2013
These items are required for the job, but are not in the truck or warehouse, so they will need to be picked up at a local supplier.
One PortaSeal™ weatherstrip
One Flexsteel™ door sweep
Three hundred sq. ft. 6 mil poly
One 100 CFM bath fan
Eight ft. of 4 in. metal duct
One 4 in. elbow
One exterior vent hood
One quart plastic roof cement
Two rolls web-type drywall tape
Four sq. ft. galvanized steel sheet metal
Twenty ft. #2 pine 1 in. x 4 in.
Eight sq. ft. 2 in. rigid foam insulation
Two Q-lon™ weatherstrips
Two Flex-steel™ door sweeps
One quart wood primer
<number>
August 2012
‹#›

## Slide 12
On Arrival
Same house…
Different season!
Photos courtesy of the US Department of Energy
GJA 2024 Version III
12
Notes: 1.7.2013
Compare the work order picture to the home. On occasion, installers have weatherized the wrong house! Don’t make that mistake!
<number>
August 2012
‹#›

## Slide 13
Crew Leader and Client
On Site: First Things First!
Photos courtesy of the US Department of Energy
GJA 2024 Version III
13
Notes: 1.7.2013
While the crew unloads the truck and sets up a reliable power source, the crew leader should walk through the home with the owner to make sure:
Homeowner understands and agrees with what is to be done.
You understand what is to be done.
Selected measures are appropriate and doable.
Any prerequisite work required of the homeowner was accomplished (e.g., moving materials out of an attic to be insulated, if this was assigned to the homeowner).
Agree on the location for lunch and breaks with the homeowner.
During this walk through with the homeowner, you will verify what the crew will be doing, identify any specific issues the residents may have (allergies, valuable items not to be moved, etc.), and obtain any necessary sign-off from the homeowner before proceeding.
<number>
August 2012
‹#›

## Slide 14
    Assess job site safety.
    Address hazards.
    Document pre-existing conditions.
    Ensure access to work areas.
    Identify potential changes to work order.
    Determine if the work schedule needs adjustment.
Purpose of Walk Through
GJA 2024 Version III
14
Notes: 1.7.2013
In addition to informing the client, the crew leader is responsible for conducting an interior and exterior pre-work home inspection to communicate with the crew about the work to be done. There are many goals to this pre-work inspection, including these related to crew communication.
Determining job site safety
Developing a site-specific safety plan to address any unsafe conditions and possible hazards
Documenting pre-existing conditions, like cracked windows or damaged interior surfaces
Ensuring accessibility to work areas
Identifying any needed change orders (covered in more detail in next exercise)
Adjusting work schedule as necessary
<number>
August 2012
‹#›

## Slide 15
In General…
GJA 2024 Version III
15
Notes: 1.7.2013
Don’t smoke in or around the client’s home.
Maintain a professional and industrious attitude for the duration.
<number>
August 2012
‹#›

## Slide 16
Site Discovered Issues
(30 Minutes)
Site-Discovered Issues -
Exercise #2
GJA 2024 Version III
16
Notes: 1.7.2013
(Refer to the Lesson Plan for instructions.)
<number>
August 2012
‹#›

## Slide 17
At the shop, review the work order:
      Check for obvious errors/oversights.
      Procure materials.
      Plan the job flow.
      At the job site, check:
      You and client understand what is to be done.
      Planned measures are doable.
      Provided materials are correct.
      Resolve any installation problems discovered on site.
Summary
GJA 2024 Version III
17
Notes: 1.7.2013
At the shop, review the work order.
Check for obvious errors/oversights.
Procure materials.
Plan the job flow.
At the job site, check to ensure that:
You and the client understand what is to be done.
Planned measures are doable.
Provided materials are correct.
Resolve any installation problems discovered on site.
Present this slide as an interactive discussion, soliciting personal examples from the trainees. Add your own personal examples and knowledge to supplement.
<number>
August 2012
‹#›